## Sheet2
Project Name | Tira Beauty | [8 empty] | Version | -
Processor+A:SB7A:M | [9 empty] | OS | Windows
RAM | - | [8 empty] | Browser | -
Module Name | Full Website
Reviewed By | Vaishali sonanis | [8 empty] | Date Reviewed on: | 2025-08-06
SR. NO. | TYPE OF TESTING | TEST CASES NO. | TEST CASE NAME | OBJECTIVE | PRE-REQUISITE | STEPS TO BE FOLLOWED | TEST DATA | EXPECTED OUTPUT | ACTUAL OUTPUT | PASSED / FAILED | BUG ID NO. | BUG ROOT CAUSE | WORK ITEM ASSOCIATED | MAJOR / MINOR BUG | IF MAJOR THEN TYPE | TESTED ON | TESTED BY | REMARKS
1 | functional testing | TR‑001 | Signup page | check wheather user is able to signup in the site or not | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. open tira site 2. goto accounts section 3. enter your phone number | 1234567892 | Invalid Phone Number | Invalid Phone Number | PASSED
2 | functional testing | TR‑002 | Signup page | check wheather user is able to signup in the site or not | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. open tira site 2. goto accounts section 3. enter your phone number | 7989867785 | ABLE TO CLICK ON SEND OTP BUTTON | ABLE TO CLICK ON SEND OTP BUTTON | PASSED
3 | functional testing | TR‑003 | TRACK ORDER MODULE | TO CHECK WHEATHER USER IS ABLE TO ACCESS TRACK ORDER OF THE PRODUCT WITHOUT SIGN IN | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. open tira site 2. goto TRACK ORDER | CLICK ON TRACK ORDER WITHOUT LOGIN | SHOULD ABLE TO SHOW SIGN UP PAGE | SHOULD ABLE TO SHOW SIGN UP PAGE | PASSED
4 | functional testing | TR‑004 | TRACK ORDER MODULE - 1 | TO CHECK WHEATHER USER IS ABLE TO ACCESS TRACK ORDER OF THE PRODUCT WITHOUT SIGN IN | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. open tira site 2. goto TRACK ORDER | CLICK ON TRACK ORDER WITHOUT LOGIN AND CLICK ON CANCEL BUTTON | SHOULD BE ABLE TO RETURN TO HOME PAGE | NOT ABLE TO RETURN TO TIRA BEAUTY | FAILED
5 | functional testing | TR‑005 | SEARCH BAR MODULE | TO CHECK WHEATHER USER IS ABLE TO GET THE RIGHT PRODUCTS AS SEARCH RESULT | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA 2. CLICK ON SEARCH AND GIVE SOME PRODUCT | LIPSTICK UNDER 500 | SHOULD BE ABLE TO SHOW ITEMS UNDER 500 | SHOWING ITEMS EVEN AFTER 500 | FAILED
6 | functional testing | TR‑006 | HOME PAGE SUBSCRIPTIONS FOR THE OFFERS IN THE TIRA | SHOULD BE ABLE TO SEND OFFERS AFTER SUBSCRIPTION | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA 2. GOTO SUBCRIPTION IN HOME PAGE GIVE YOUR VALID MAIL | SAIKARTHIK573@GMAIL.COM | ABLE TO SEND OFFERS TO THE CUSTOMERS | ABLE TO SEND OFFERS TO THE CUSTOMERS | PASSED
7 | functional testing | TR‑007 | HOME PAGE SUBSCRIPTIONS FOR THE OFFERS IN THE TIRA | SHOULD BE ABLE TO SEND OFFERS AFTER SUBSCRIPTION | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA 2. GOTO SUBCRIPTION IN HOME PAGE GIVE YOUR VALID MAIL | 123@GMAIL.COM | ABLE TO SHOW TO USER TO ENTER VALID EMAIL | ACCEPTING EMAIL WITOUT VERIFICATION | FAILED
8 | functional testing | TR‑008 | RESPONSIVENESS OF THE WEBSITE | SHOULD BE ABLE TO SHOW THE SITE WITHOUT ANY ISSUE | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA SITE IN ANY DEVICE LIKE PHONE | 1. OPEN TIRA SITE IN ANY DEVICE LIKE PHONE 2. GOTO PRODUCT LIST PAGE | ABLE TO SHOW TO USER THE ENTIRE PAGE | IT IS NOT SHOWING SOCIAL MEDIA ICONS | FAILED
9 | functional testing | TR‑009 | ACCOUNT SECITON in personal details | SHOULD BE ABLE TO enter correct details firstname | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA SITE 2. LOGIN YOUR ACCOUNT 3. GOTO ACCOUNTS 4. enter firstname | kira | able to take the string | able to take the string | passed
10 | functional testing | TR‑010 | ACCOUNT SECITON in personal details | SHOULD BE ABLE TO enter correct details firstname | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA SITE 2. LOGIN YOUR ACCOUNT 3. GOTO ACCOUNTS 4. enter firstname | kira112 | tell user to enter only name string | taking everything | FAILED
11 | functional testing | TR‑011 | ACCOUNT SECITON in personal details | SHOULD BE ABLE TO enter correct details lastname | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA SITE 2. LOGIN YOUR ACCOUNT 3. GOTO ACCOUNTS 4. enter lastname | kun | tell user to enter only name string | taking name | passed
12 | functional testing | TR‑012 | ACCOUNT SECITON in personal details | SHOULD BE ABLE TO enter correct details lastname | 1. stable internet connection 2. tira site link 3. mobile or laptop 4. brower like chrome or edge or any other | 1. OPEN TIRA SITE 2. LOGIN YOUR ACCOUNT 3. GOTO ACCOUNTS 4. enter lastname | kira132 | tell user to enter only name string | taking everything | FAILED

## Sheet3
Section | Details
Project Name | EBAY
Module Name | REGISTER/LOGIN
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | KARTHIK
Date | 2025-07-08
1. Test Summary
Metric | Count
Total Test Cases | 12
Executed Test Cases | 12
Passed Test Cases | 6
Failed Test Cases | 6
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | YES
Manual Test Cases | 12
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 6 | 50%
Failed | 6 | 50%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 12
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 4
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 9 out of 9 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
check all the defects and try to resolve those issues and track order section in the home page cancel button is not working and it might effect the user experience when he visits the site for the first time
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
username and password easily available | Medium | Open | hide username and password
after login it will show this "This site can’t provide a secure connection" so this create confusion | Medium | Open | redirect to Home page
7. Recommendations
VERIFY FIELDS IN LOGIN PAGE
VERIFY FIELDS IN REGISTRATION PAGE

## Sheet1
ØDefect identifier | Def_login_001 | Def_login_002 | Def_login_003 | Def_login_004 | Def_login_005
ØDefect summary | Respoiveness of website in the product list page expected -> social media icons should be visible at the end of the page . Actual -> social media icons are not visible in the page they are placed in the back of filter button. | validation of email address in the home page for sending the mail FOR ANY NEW OFFERS if there is any discount of any product. EXPECTED -> ENTER A VALID EMAIL ADDRESS . ACTUAL -> EMAIL SUBSCRIBED SUCCESSFULLY | GO TO THE PRODUCT PAGE AND CHECK FOR THEADDRESS AND CHECK THE LOCATION UNABLE TO FETCH THE LOCATION OF THE USER EXPECTED -> SHOW THE LOCATION OF THE USER ACTUAL -> UNABLE TO FETCH THE LOCATION OF THE USER | unable to return back to the home page if we click on the cancel button in the track order module. WHEN THE USER NOT CREATED ACCOUNT | unable to get the correct results in the search for prices expected -> LIPSTICKS UNDER 1500 ACTUAL -> LIPSTICKS COMING ABOVE 1500 ALSO
ØTest Id | TC‑001 | TC‑002 | TC‑003 | TC‑004 | TC‑005
ØTest case name | TC_RESPOSIVNESS | TC_EMAIL | TC_LOCATION | TC_TRACK_ORDER | TC_SEARCH_BAR
ØModule name | TC_PRODUCT_LIST_PAGE | TC_EMAIL | TC_LOCATION | TC_TRACK_ORDER | TC_SEARCH_BAR
Øreproducible | SEEARCH ON ANY PRODUCT AND SCROOL DOWN TO SEE SOCIAL MEDIA ICONS IN MOBILE | ENTER ANY DATA LIKE 123@GMAIL.COM | GO TO THE PRODUCT PAGE AND CHECK FOR THEADDRESS AND CHECK THE LOCATION UNABLE TO FETCH THE LOCATION OF THE USER | GO TO TRACK ORDER PAGE AND CLICK ON THE CANCEL BUTTON | GO TO SEARCH BAR AND TYPE ANY PRODUCT UNDER SOME PRICE
Øseverity | LOW | MEDIUM | MEDIUM | MEDIUM | MEDIUM
Øpriority | LOW | MEDIUM | MEDIUM | MEDIUM | MEDIUM
ØRaised by | VENKATA SAI SRI KARTHIK(TESTER NAME) | VENKATA SAI SRI KARTHIK(TESTER NAME) | VENKATA SAI SRI KARTHIK(TESTER NAME) | VENKATA SAI SRI KARTHIK(TESTER NAME) | VENKATA SAI SRI KARTHIK(TESTER NAME)
ØAssigned to | Reeva Shah(TL name) | Reeva Shah(TL name) | Reeva Shah(TL name) | Reeva Shah(TL name) | Reeva Shah(TL name)
ØDate of assignment | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-09
Østatus | OPEN | OPEN | OPEN | OPEN | OPEN
ØSnap shots
ØFixed by | NA | NA | NA | NA | NA
ØDate of fixing=
ØApprovals=manager name | VISHALI (MANAGER) | VISHALI (MANAGER) | VISHALI (MANAGER) | VISHALI (MANAGER) | VISHALI (MANAGER)